## ToDo
Task Name | Description | Assigned To | Due Date | Status | Priority | Category
Create Business Plan | Develop a comprehensive business plan | Anda | 2023-06-01 | Not Started | High | Planning
Market Research: Competitors & Target Customers | Analyze competitors and define target audience | Anda | 2023-06-15 | Not Started | High | Research
Obtain business license | Register business with local authorities | Anda | 2023-05-20 | Not Started | Critical | Legal
Find suitable location | Scout and secure bakery location | Anda | 2023-06-30 | Not Started | High | Operations
Design bakery layout | Plan interior design and workflow | Anda | 2023-07-15 | Not Started | Medium | Design
Hire initial staff | Recruit and train bakery staff | Anda | 2023-08-01 | Not Started | High | HR
Marketing strategy development | Create comprehensive marketing plan | Anda | 2023-06-20 | Not Started | Medium | Marketing

## Dashboard
Metric Type | Category | Value | Percentage | Last Updated | Trend
Task Status | Not Started | 7 | 46.7 | 2023-05-25 | Stable
Task Status | In Progress | 4 | 26.7 | 2023-05-25 | Increasing
Task Status | Completed | 5 | 33.3 | 2023-05-25 | Increasing
Budget Status | Allocated | 14000000 | 100 | 2023-05-25 | Stable
Budget Status | Spent | 0 | 0 | 2023-05-25 | Stable
Budget Status | Remaining | 14000000 | 100 | 2023-05-25 | Stable
Risk Level | Critical | 1 | 12.5 | 2023-05-25 | Stable
Risk Level | High | 3 | 37.5 | 2023-05-25 | Stable
Risk Level | Medium | 4 | 50 | 2023-05-25 | Stable
Timeline Status | On Track | 6 | 66.7 | 2023-05-25 | Good
Timeline Status | At Risk | 2 | 22.2 | 2023-05-25 | Warning
Timeline Status | Delayed | 1 | 11.1 | 2023-05-25 | Alert

## Growth
Strategy ID | Strategy | Timeline | Responsible Person | Progress (%) | Investment Required | Expected ROI | Status
G001 | Partner with GoFood / GrabFood | Q3 2023 | Anda | 0 | 500000 | 150% | Planning
G002 | Expand product line | Q4 2023 | Anda | 0 | 1000000 | 120% | Planning
G003 | Catering services launch | Q1 2024 | Anda | 0 | 800000 | 200% | Planning
G004 | Second location scouting | Q2 2024 | Anda | 0 | 5000000 | 180% | Planning
G005 | Corporate partnerships | Q3 2024 | Anda | 0 | 300000 | 250% | Planning
G006 | Franchise development | Q1 2025 | Anda | 0 | 2000000 | 300% | Planning

## LaunchPlan
Step ID | Step | Responsible Person | Deadline | Status | Prerequisites | Notes
L001 | Soft Launch (Friends/Family) | Anda | 2023-07-01 | Not Started | Menu finalized | Invite 20-30 people
L002 | Staff final training | Anda | 2023-06-25 | Not Started | Staff hired | 2-day intensive training
L003 | Menu pricing finalization | Anda | 2023-06-20 | Not Started | Cost analysis done | Include profit margins
L004 | Social media campaign launch | Anda | 2023-06-30 | Not Started | Branding complete | Instagram Facebook TikTok
L005 | Grand opening event | Anda | 2023-07-15 | Not Started | Soft launch complete | Public launch event
L006 | Local media outreach | Anda | 2023-07-10 | Not Started | Press kit ready | Contact local newspapers
L007 | Customer feedback collection | Anda | 2023-07-20 | Not Started | Launch complete | Survey and review system

## Risks
Risk ID | Risk Description | Likelihood | Impact | Risk Score | Mitigation Strategy | Status | Owner | Review Date
R001 | Supplier delays | Medium | High | 6 | Identify backup suppliers | Monitoring | Anda | 2023-06-01
R002 | Equipment breakdown | Low | High | 4 | Maintenance contracts and backup equipment | Monitoring | Anda | 2023-06-15
R003 | Staff turnover | Medium | Medium | 4 | Competitive compensation and training | Monitoring | Anda | 2023-07-01
R004 | Economic downturn | Medium | High | 6 | Diversify revenue streams | Monitoring | Anda | 2023-06-01
R005 | Competition increase | High | Medium | 6 | Focus on unique value proposition | Monitoring | Anda | 2023-05-15
R006 | Regulatory changes | Low | Medium | 2 | Stay updated with regulations | Monitoring | Anda | 2023-08-01
R007 | Supply cost inflation | High | High | 9 | Long-term supplier contracts | Critical | Anda | 2023-05-20
R008 | Customer preference changes | Medium | Medium | 4 | Regular market research | Monitoring | Anda | 2023-07-15

## Timeline
Milestone | Start Date | End Date | Duration | Status | Dependencies | Critical Path
Create Business Plan | 2023-06-01 | 2023-06-30 | 29 | Not Started |  | Yes
Market Research | 2023-05-01 | 2023-06-15 | 45 | In Progress |  | Yes
Equipment Procurement | 2023-05-15 | 2023-06-30 | 46 | In Progress | Market Research | Yes
Location Setup | 2023-06-01 | 2023-07-15 | 44 | Not Started | Business Plan | Yes
Staff Recruitment | 2023-06-15 | 2023-08-01 | 47 | Not Started | Location Setup | No
Menu Development | 2023-05-01 | 2023-06-30 | 60 | In Progress |  | Yes
Marketing Campaign | 2023-06-20 | 2023-07-15 | 25 | Not Started | Menu Development | No
Soft Launch | 2023-07-01 | 2023-07-07 | 6 | Not Started | Location Setup | Yes
Grand Opening | 2023-07-15 | 2023-07-15 | 0 | Not Started | Soft Launch | Yes

## Budget
Item Category | Estimated Cost | Actual Cost | Remaining Budget | Notes | Status
Ingredients & Supplies | 2000000 | 0 | 2000000 | Flour eggs sugar etc. | Planned
Basic Equipment | 4000000 | 0 | 4000000 | Oven mixer utensils | Planned
Renovation & Interior | 3000000 | 0 | 3000000 | Flooring lighting furniture | Planned
Marketing & Branding | 1500000 | 0 | 1500000 | Logo design signage website | Planned
Business License & Legal | 500000 | 0 | 500000 | Permits registration fees | Planned
Initial Inventory | 1000000 | 0 | 1000000 | Packaging materials supplies | Planned
Staff Training | 800000 | 0 | 800000 | Training programs certification | Planned
Contingency Fund | 1200000 | 0 | 1200000 | Emergency expenses buffer | Planned

## InProgress
Task Name | Description | Assigned To | Start Date | Due Date | Progress (%) | Status Update | Last Updated
Finalizing menu recipes | Testing and perfecting recipes | Anda | 2023-05-01 | 2023-05-31 | 50 | Half of the recipes are finalized | 2023-05-15
Equipment procurement | Sourcing and purchasing bakery equipment | Anda | 2023-05-15 | 2023-06-15 | 25 | Comparing suppliers and prices | 2023-05-20
Logo and branding design | Creating visual identity for bakery | Anda | 2023-05-10 | 2023-06-10 | 75 | Logo concepts ready for final review | 2023-05-25
Location negotiations | Finalizing lease agreement | Anda | 2023-05-20 | 2023-06-20 | 30 | Reviewing contract terms | 2023-05-22

## Completed
Task Name | Completion Date | Notes | Duration (Days) | Category
Registered domain name | 2023-04-15 | www.sweetbakery.com | 1 | Digital
Created Instagram account | 2023-04-20 | @sweetbakery | 1 | Marketing
Initial market research | 2023-04-25 | Identified target demographics | 7 | Research
Business concept development | 2023-04-30 | Finalized bakery concept and vision | 5 | Planning
Competitor analysis | 2023-05-05 | Analyzed 10 local competitors | 3 | Research